## Sheet1
Sl Number/ ID | User Story / Feature | Priority | Story Points | Status (Completed / Not Completed) | Sprint | Assigned to | Notes / Comments | Date
1 | * Dairy feature | 10 | 15 | Completed | 2 | Team | Completed on 17/09/25 | 2025-09-09
2 | * Authentication | 5 | 15 | Completed | 2 | Team | Completed on 17/09/25 | 2025-09-09
3 | * Chatbot (API Integration) | 10 | 15 | Completed | 2 | Team | Completed on 17/09/25 | 2025-09-09
4 | * Avatar implementation | 4 | 8 | Not completed | 7 | Team | -
5 | * Dashboard UI/UX | 4 | 8 | Not completed | 7 | Team | -